## Dashboard
[23 empty] | Rating | Risks
[23 empty] | Low | 0
[23 empty] | Moderate | 0
GRC PROJECT 01 / EXECUTIVE WORKSPACE / TRAINING SCENARIO | [22 empty] | High | 4
[6 empty] | VALIDATION STATUS | [7 empty] | INHERENT RATING | [8 empty] | Critical | 0
[6 empty] | All | [7 empty] | All
Risk filters apply to the risk cards, distribution and heatmap. Evidence and action summaries include all records.
[23 empty] | Evidence stage | Requests
RISKS IN VIEW | [5 empty] | HIGH / CRITICAL | [5 empty] | VALIDATED IN VIEW | [5 empty] | PENDING VALIDATION |  |  |  |  | Planned | 4
[23 empty] | Requested | 0
4 | [5 empty] | 4 | [5 empty] | 0 | [5 empty] | 4 |  |  |  |  | Received | 0
[23 empty] | In review | 0
[23 empty] | Reviewed | 0
INHERENT RISK DISTRIBUTION | [11 empty] | LIKELIHOOD × IMPACT
[23 empty] | 6 | 12 | 20
[16 empty] | 1 | 2 | 3 | 4 | 5 |  |  | High
[15 empty] | 5 | 0 | 0 | 0 | 0 | 0
[15 empty] | 4 | 0 | 0 | 0 | 0 | 0
[15 empty] | 3 | 0 | 0 | 0 | 4 | 0 |  |  | 1
[15 empty] | 2 | 0 | 0 | 0 | 0 | 0
[15 empty] | 1 | 0 | 0 | 0 | 0 | 0
Rows: likelihood 5 → 1. Columns: impact 1 → 5. Each cell counts risks; color reflects the score band.
Risk distribution total: 4 / 4 risks in view
[12 empty] | SELECT RISK ID | SELECT RISK | SELECT RISK | SELECT RISK | SELECT RISK | SELECT RISK | R-001 | R-001 | R-001 | R-001 | R-001
EVIDENCE COLLECTION | [11 empty] | Missing MFA / ASSESSMENT SNAPSHOT | [10 empty] | 120100
120099
[12 empty] | Missing MFA | [6 empty] | 12 / High |  |  |  | 120098
120097
0
[12 empty] | Validation: Pending validation. Owner: Security owner - proposed. Workflow: Proposed. See the scorecard and actions below for evidence and approval needs. | [10 empty] | 0
0
0
0
[12 empty] | VALIDATED EVIDENCE | [9 empty] | 0 | 0
[12 empty] | OVERDUE ACTIONS | [9 empty] | 0 | 0
0
0
ASSESSMENT WORKSPACE / Risk cards and heatmap follow the filters above. Progress, insights and action priorities below include all records. Planned requests and completed actions do not establish verified closure. | [22 empty] | 0
0
0
ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | ASSESSMENT READINESS / ALL RECORDS | 0
0
CONTROLS ASSESSED | CONTROLS ASSESSED | CONTROLS ASSESSED | CONTROLS ASSESSED | CONTROLS ASSESSED |  | EVIDENCE REVIEWED | EVIDENCE REVIEWED | EVIDENCE REVIEWED | EVIDENCE REVIEWED | EVIDENCE REVIEWED |  | CLOSURES VERIFIED | CLOSURES VERIFIED | CLOSURES VERIFIED | CLOSURES VERIFIED | CLOSURES VERIFIED |  | UNSCHEDULED ACTIONS | UNSCHEDULED ACTIONS | UNSCHEDULED ACTIONS | UNSCHEDULED ACTIONS | UNSCHEDULED ACTIONS | 0
0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 4 |  |  |  |  | 0
0
0
EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | EXECUTIVE INSIGHTS | 0
4 risks recorded; 4 await validation. 4 controls have no design assessment; 4 have no operating assessment. | [22 empty] | 0
0
4 evidence requests remain planned; 0 are reviewed. 4 actions await approval; 4 open actions have no target date. | [22 empty] | 0
0
SIGN-OFF PENDING / Evidence, assessment and approval prerequisites remain open. Verified closure requires approval, a valid completion date and reviewed, validated evidence linked to the same risk. | [22 empty] | 0
0
TRACEABILITY ALERT / 0 risk records lack evidence IDs. Approval must precede scheduling and implementation. | [22 empty] | 0
RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | RISK SCORECARD / FIRST 10 REGISTERED RISKS | 0
Risk ID | Risk ID | Risk title | Risk title | Risk title | Risk title | Risk title | Inherent | Inherent | Validation | Validation | Validation | Validation | Controls assessed | Controls assessed | Controls assessed | Evidence reviewed | Evidence reviewed | Evidence reviewed | Actions verified | Actions verified | Actions verified | Actions verified | 0
R-001 |  | Missing MFA |  |  |  |  | 12 / High |  | Pending validation |  |  |  | 0 / 1 |  |  | 0 / 1 |  |  | 0 / 1 |  |  |  | 0
R-002 |  | Excessive Access Permissions |  |  |  |  | 12 / High |  | Pending validation |  |  |  | 0 / 1 |  |  | 0 / 1 |  |  | 0 / 1 |  |  |  | 0
R-003 |  | Shared Administrator Accounts |  |  |  |  | 12 / High |  | Pending validation |  |  |  | 0 / 1 |  |  | 0 / 1 |  |  | 0 / 1 |  |  |  | 0
R-004 |  | Missing Formal Cybersecurity Risk Register |  |  |  |  | 12 / High |  | Pending validation |  |  |  | 0 / 1 |  |  | 0 / 1 |  |  | 0 / 1 |  |  |  | 0
0
0
0
0
0
0
0
EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE | EVIDENCE PIPELINE |  | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | REMEDIATION PROGRESS | 0
Planned request | Planned request | Planned request | Planned request | Planned request | Planned request | Planned request | Planned request | 4 |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 4 |  |  | 0
Requested | Requested | Requested | Requested | Requested | Requested | Requested | Requested | 0 |  |  |  | Open | Open | Open | Open | Open | Open | Open | Open | 0 |  |  | 0
Received | Received | Received | Received | Received | Received | Received | Received | 0 |  |  |  | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | 0 |  |  | 0
Under review | Under review | Under review | Under review | Under review | Under review | Under review | Under review | 0 |  |  |  | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | 0 |  |  | 0
Reviewed | Reviewed | Reviewed | Reviewed | Reviewed | Reviewed | Reviewed | Reviewed | 0 |  |  |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 |  |  | 0
Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. |  | Completed = implementation recorded. Verified = approved action, valid completion date and validated closure, supported by one unique, reviewed and validated evidence record for the same risk, with received date, location and reviewer. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | 0
Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. | Stages reflect request workflow. Reviewed evidence still requires a supported validation conclusion. |  | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | Completed = implementation recorded. Verified = approval + completion date + evidence IDs + validated closure. | 0
[12 empty] | Approved actions: 0 / 4 total actions | [10 empty] | 0
PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | PRIORITY ACTIONS / TOP 10 UNVERIFIED ACTIONS | 0
Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | Ranked by inherent risk score, then overdue status; source order breaks ties. Missing target dates are shown explicitly. | 0
Action / Risk | Action / Risk | Proposed owner | Proposed owner | Proposed owner | Proposed owner | Proposed owner | Risk score | Risk score | Approval | Approval | Approval | Approval | Workflow | Workflow | Workflow | Target date | Target date | Target date | Next prerequisite | Next prerequisite | Next prerequisite | Next prerequisite | 0
A-001 / R-001 |  | Security owner - proposed |  |  |  |  | 12 |  | Pending approval |  |  |  | Proposed |  |  | Not scheduled |  |  | Obtain approval |  |  |  | 0 | 1
A-002 / R-002 |  | IT / IAM Administrator - proposed |  |  |  |  | 12 |  | Pending approval |  |  |  | Proposed |  |  | Not scheduled |  |  | Obtain approval |  |  |  | 0 | 2
A-003 / R-003 |  | Sentinel IAM Administrator - proposed |  |  |  |  | 12 |  | Pending approval |  |  |  | Proposed |  |  | Not scheduled |  |  | Obtain approval |  |  |  | 0 | 3
A-004 / R-004 |  | IT Security Manager - Proposed |  |  |  |  | 12 |  | Pending approval |  |  |  | Proposed |  |  | Not scheduled |  |  | Obtain approval |  |  |  | 0 | 4
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[23 empty] | 0 | 0
0
Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | Training scenario / Provisional risk ratings are not organization-wide maturity scores. No maturity percentage is inferred. | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Sentinel Defense Solutions
CYBERSECURITY
GRC PORTFOLIO
01 Dashboard
02 Risk register
03 Controls
04 Evidence
05 Remediation
06 Scoring
07 Guide

## Risk Register
GRC PROJECT 01 / TRAINING WORKSPACE / FOUR SIMULATED RISKS / EVIDENCE AND APPROVAL PENDING
Risk ID | Risk title | Scenario fact / source | Unverified assumptions | Scope / asset | Category | Likelihood | Impact | Inherent score | Inherent rating | Proposed owner | Treatment | Validation status | Workflow status | Evidence IDs | Residual likelihood | Residual impact | Residual score | Residual rating | Assessment notes | Dashboard included
R-001 | Missing MFA | Sentinel Defense Solutions' fictional case study identifies that some employees do not have multifactor authentication (MFA) enabled. Source: Project 01 fictional case study. The number of affected accounts and whether privileged accounts are included have not been established. | The number and roles of accounts without MFA, identity provider configuration, MFA enforcement policies, exceptions, compensating controls, and historical authentication activity have not been verified. No account compromise or data breach has been established. | Pending scope confirmation | Identity and access | 3 | 4 | 12 | High | Security owner - proposed | Mitigate | Pending validation | Proposed | E-001 |  |  |  |  | Provisional assessment: Likelihood 3/5 (Possible) and Impact 4/5 (Major), resulting in a High risk score of 12/25. Inconsistent MFA enforcement increases the possibility of unauthorized account access if credentials are compromised. Potential consequences include exposure of sensitive records, operational disruption, and contractual or financial impacts. Recommend enforcing MFA across applicable accounts, prioritizing privileged access, reviewing approved exceptions, and monitoring authentication activity. Validate through identity-provider configurations, account-level MFA coverage reports, exception records, and relevant authentication logs. No compromise or confirmed control failure beyond the stated MFA gap has been established. | 1
R-002 | Excessive Access Permissions | Sentinel Defense Solutions' fictional case scenario identifies concerns that some employees may have access to files beyond their assigned job responsibilities. Source: Project 01 fictional case study. | The number of affected employees, specific file repositories, actual permission assignments, sensitivity of accessible records, effectiveness of existing access controls, and frequency of access reviews have not been verified. | Proposed scope: file repositories containing customer records, employee PII, and contract documentation. Actual repositories, affected users, permission assignments, and data sensitivity require confirmation. | Identity and access | 3 | 4 | 12 | High | IT Security Manager - proposed | Mitigate | Pending validation | Proposed | E-002 |  |  |  |  | Provisional assessment: Likelihood 3/5 (Possible) and Impact 4/5 (Major), resulting in a High risk score of 12/25. Suspected excessive permissions could allow employees or compromised accounts to access, modify, or disclose sensitive information beyond legitimate business requirements. Recommend validating current permissions against documented job responsibilities, removing unjustified access, enforcing least privilege, and establishing periodic access reviews. Request permission exports, role definitions, access approvals, group memberships, and prior review records. The extent of excessive access, effectiveness of existing controls, and any actual unauthorized disclosure remain unverified. | 1
R-003 | Shared Administrator Accounts | Sentinel Defense Solutions' fictional case study states that an external IT support vendor uses shared administrator accounts. Source: Project 01 fictional case study. The account privileges, number of users, affected systems, and existing safeguards have not been established. | The number and identities of vendor personnel using shared administrator accounts, account privileges, affected systems, MFA enforcement, credential-management practices, activity attribution, access approvals, and existing monitoring controls have not been verified. No account compromise, misuse, or security incident has been established. | Proposed scope: shared vendor administrator accounts, systems managed by the external IT provider, and information accessible through those systems. Actual access scope and data sensitivity require confirmation. | Identity and access | 3 | 4 | 12 | High | IT Security Manager - Proposed | Mitigate | Pending validation | Proposed | E-003 |  |  |  |  | Provisional assessment: Likelihood 3/5 (Possible) and Impact 4/5 (Major), resulting in a High risk score of 12/25. Shared administrator accounts used by an external IT support vendor may reduce individual accountability and complicate access revocation. Unauthorized use or compromise of privileged credentials could result in system changes, disclosure of accessible information, or operational disruption. Recommend confirming account scope and authorized users, replacing shared access with individually attributable privileged identities where feasible, enforcing appropriate MFA and least privilege, and reviewing privileged activity monitoring. Validate using privileged-account inventories, vendor access approvals, account permissions, MFA configurations, and dated administrative activity records. No unauthorized activity or incident has been established. | 1
R-004 | Missing Formal Cybersecurity Risk Register | Sentinel Defense Solutions' fictional case study states that the organization does not have a documented cybersecurity risk register. Source: Project 01 fictional case study. The existence and effectiveness of other risk management activities have not been established. | Existing risk identification practices, departmental risk records, risk ownership assignments, assessment methodology, review frequency, escalation procedures, management reporting, treatment approvals, and risk acceptance authority have not been verified. The duration of the documented-register gap and any resulting incidents or losses are unknown. | Enterprise cybersecurity risk identification, assessment, ownership, prioritization, treatment tracking, escalation, and leadership reporting across Sentinel operations and relevant third-party relationships. Actual process coverage and existing safeguards require confirmation. | Governance | 3 | 4 | 12 | High | IT Security Manager - Proposed | Mitigate | Pending validation | Proposed | E-004 |  |  |  |  | Provisional assessment: Likelihood 3/5 (Possible) and Impact 4/5 (Major), resulting in a High risk score of 12/25. The absence of a documented cybersecurity risk register may limit consistent identification, prioritization, ownership, escalation, and monitoring of cybersecurity risks. A material risk could consequently be overlooked or addressed late, potentially contributing to operational disruption, financial loss, or contractual consequences. Recommend establishing a formal enterprise cybersecurity risk register supported by documented assessment criteria, assigned risk owners, treatment decisions, periodic reviews, escalation thresholds, and management reporting. Validate through existing policies, risk records, leadership meeting records, assigned responsibilities, and evidence of risk review and escalation practices. Other governance processes, actual consequences, and control effectiveness remain unverified. | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
RISK REGISTER
CYBERSECURITY
GRC PORTFOLIO
01 Dashboard
02 Risk register
03 Controls
04 Evidence
05 Remediation
06 Scoring
07 Guide

## Control Assessment
GRC PROJECT 01 / TRAINING WORKSPACE / CONTROL ASSESSMENT / EVIDENCE AND APPROVAL PENDING
Control ID | Risk ID | Proposed control objective | Design test plan | Operating test plan | Design result | Operating result | Evidence IDs | Assessor | Assessment date | Validation status | Facts / assumptions / notes
C-001 | R-001 | Enforce MFA on all applicable employee and privileged accounts, with documented exceptions and approved compensating safeguards where necessary. | Review the MFA policy, identity-provider configurations, enforcement scope, privileged-account requirements, exception register, and approved compensating safeguards. Determine whether the proposed design requires MFA for all applicable accounts and defines appropriate exception approval and review procedures. | After confirming the assessment period and account population, select and document a sample covering employee, privileged, newly created, and exception accounts where applicable. Inspect dated authentication records and account-level configurations to verify MFA enforcement throughout the period. Check that exceptions were authorized and compensating safeguards operated as approved. Record results and exceptions against predefined criteria. | Not assessed | Not assessed | E-001 |  |  | Pending validation | All control details and tests are proposals. No control failure or effectiveness conclusion has been validated.
C-002 | R-002 | Restrict access to sensitive files according to approved job responsibilities and least-privilege principles. | Review access-control policies, role definitions, approval workflows, and permission configurations to determine whether the proposed controls would restrict unnecessary access. | After scope confirmation, sample employee accounts and sensitive folders. Compare actual permissions against approved roles and access requests; inspect dated access reviews and remediation records. | Not assessed | Not assessed | E-002 |  |  | Pending validation | Proposed least-privilege control. Existing permission restrictions, approval processes, and review effectiveness have not been verified. No control test has been performed.
C-003 | R-003 | Ensure external IT vendor administrators use individually attributable, approved privileged access with MFA, least-privilege permissions, and appropriate activity logging and monitoring. Shared administrator credentials should be eliminated where feasible or subject to documented, approved safeguards. | Review the vendor access policy, privileged-account inventory, administrator identity configurations, role definitions, MFA requirements, and access approval procedures. Compare documented requirements and configurations against the control objective to determine whether individual accountability, least privilege, and appropriate safeguards are adequately designed. | After defining the assessment period and population, select a documented sample of vendor administrator accounts and privileged sessions. Compare each sampled account with approved access records, assigned roles, MFA enforcement records, and privileged activity logs. Determine whether access was individually attributable, authorized, appropriately restricted, and monitored. Record exceptions against predefined criteria. | Not assessed | Not assessed | E-003 |  |  | Pending validation | Proposed privileged-access control and test procedures. The fictional scenario establishes use of shared vendor administrator accounts, but actual account privileges, authorized users, MFA enforcement, and monitoring practices remain unverified. No design or operating effectiveness testing has been performed.
C-004 | R-004 | Establish and maintain a documented enterprise cybersecurity risk management process and centralized risk register that records identified risks, likelihood and impact assessments, assigned risk owners, treatment decisions, approval status, review dates, escalation criteria, and management reporting. | Review the documented cybersecurity risk management policy, risk assessment methodology, risk register template, ownership requirements, risk acceptance authority, review schedule, escalation criteria, and management reporting procedures. Determine whether the proposed process is adequately designed to identify, assess, assign, prioritize, treat, monitor, and report cybersecurity risks. | After establishing the assessment period and risk population, select a documented sample of cybersecurity risks. Verify that each sampled risk has an assessment, assigned owner, documented treatment decision, appropriate approvals, and evidence of periodic review or escalation where required. Compare sampled records against management reports and supporting documentation; record exceptions against predefined criteria. | Not assessed | Not assessed | E-004 |  |  | Pending validation | Proposed enterprise cybersecurity risk management control and test procedures. The fictional scenario confirms that Sentinel lacks a documented cybersecurity risk register, but existing alternative risk management activities have not been assessed. No control design or operating effectiveness testing has been performed. Control ownership, approval, and implementation remain unverified.
CONTROL ASSESSMENT
CYBERSECURITY
GRC PORTFOLIO
01 Dashboard
02 Risk register
03 Controls
04 Evidence
05 Remediation
06 Scoring
07 Guide

## Evidence Tracker
GRC PROJECT 01 / TRAINING WORKSPACE / FOUR SIMULATED RISKS / EVIDENCE AND APPROVAL PENDING
Evidence ID | Risk ID | Control ID | Requested evidence | Purpose / proposed coverage | Custodian | Request date | Due date | Received date | Status | Evidence location | Reviewer | Validation status | Review notes
E-001 | R-001 | C-001 | MFA policy, identity-provider enforcement configurations, account-level MFA coverage report, privileged-account coverage, approved exception register, compensating-control documentation, and dated authentication records. | Confirm scope; evaluate design and operating effectiveness. Sampling population and period remain unverified. | IT / Identity Administrator - proposed |  |  |  | Planned request |  |  | Pending validation | No evidence received or reviewed. E-001 identifies a planned request only.
E-002 | R-002 | C-002 | Current file-permission and group-membership exports, role definitions, approved access requests, historical permission-change records where available, and dated access-review results. | Determine whether permissions to sensitive files align with approved job responsibilities and whether unnecessary access is identified and removed. | IT / IAM Administrator - proposed, pending confirmation |  |  |  | Planned request |  |  | Pending validation | Evidence has not been requested, received, or reviewed. Scope, affected repositories, permissions, and access-review effectiveness remain unverified.
E-003 | R-003 | C-003 | Privileged-account inventory; vendor administrator personnel roster; account-to-user mappings; role and permission exports; vendor access approval records; MFA enforcement configurations and dated sign-in records; privileged session/activity logs; and documented shared-account exceptions or compensating safeguards, if applicable. | Determine whether vendor administrator access is individually attributable, authorized, restricted by least privilege, protected by MFA, and appropriately monitored. Confirm affected systems, account population, and assessment period before testing. Evaluate approved exceptions and compensating safeguards where shared accounts remain necessary. | Sentinel IT / IAM Administrator and external IT vendor administrator - proposed, pending confirmation. |  |  |  | Planned request |  |  | Pending validation | Planned evidence request only. No evidence has been requested, received, or reviewed. Before testing, confirm source-system coverage, record dates, completeness, and reliability; reconcile vendor records with Sentinel account inventories and approvals; investigate missing or inconsistent records. No control effectiveness conclusion has been reached.
E-004 | R-004 | C-004 | Cybersecurity risk management policies and procedures; existing departmental risk lists or risk records; risk assessment methodology and scoring criteria; risk ownership assignments; treatment and risk acceptance approval records; risk review schedules and meeting minutes; escalation procedures; management risk reports; and relevant third-party risk management records, if available. | Determine whether Sentinel has documented or alternative practices for identifying, assessing, assigning, treating, escalating, monitoring, and reporting cybersecurity risks. Establish the relevant process population and assessment period, evaluate the completeness and reliability of available records, and identify governance gaps requiring remediation. | Sentinel IT Security Manager and relevant business or risk management representatives - proposed, pending confirmation. |  |  |  | Planned request |  |  | Pending validation | Planned evidence request only. No evidence has been requested, received, or reviewed. The fictional scenario confirms the absence of a documented cybersecurity risk register, but other risk management practices remain unverified. Confirm record ownership, completeness, dates, approvals, and source reliability before testing. No design or operating effectiveness conclusion has been reached.
EVIDENCE TRACKER
CYBERSECURITY
GRC PORTFOLIO
01 Dashboard
02 Risk register
03 Controls
04 Evidence
05 Remediation
06 Scoring
07 Guide

## Remediation Tracker
GRC PROJECT 01 / TRAINING WORKSPACE / FOUR SIMULATED RISKS / EVIDENCE AND APPROVAL PENDING
Action ID | Risk ID | Proposed action | Proposed owner | Approval status | Workflow status | Target date | Completed date | Closure evidence ID | Closure validation | Days overdue | Notes / dependencies
A-001 | R-001 | Confirm MFA coverage and approved exceptions; enforce MFA on applicable employee and privileged accounts; implement approved compensating safeguards where exceptions are necessary; verify enforcement using updated configurations and account-level coverage reports. | Security owner - proposed | Pending approval | Proposed |  |  |  | Pending validation |  | Confirm identity-provider scope, affected accounts, privileged access, and approved exceptions. Obtain risk-owner approval and assign implementation responsibility before scheduling changes. No corrective action or independent closure verification has occurred.
A-002 | R-002 | Review access permissions against approved job responsibilities; identify and remove unjustified access following authorization; establish periodic access reviews; independently verify corrected permissions. | IT / IAM Administrator - proposed | Pending approval | Proposed |  |  |  | Pending validation |  | Confirm affected repositories and roles; obtain data owner approval for access changes; document authorized exceptions, establish review frequency and closure criteria. No remediation has been performed or verified.
A-003 | R-003 | Confirm the population and scope of vendor privileged accounts; replace shared administrator access with individually attributable, approved accounts where feasible; enforce MFA and least-privilege permissions; disable or appropriately safeguard legacy shared credentials; implement privileged activity logging, periodic access reviews, and timely access revocation. Independently verify the implemented changes before recommending closure. | Sentinel IAM Administrator - proposed | Pending approval | Proposed |  |  |  | Pending validation |  | Confirm affected systems, vendor administrator roster, technical compatibility, and operational support requirements. Obtain risk owner and applicable system-owner approvals before implementation. Coordinate changes with the external IT vendor to prevent service disruption. Define approved exceptions and compensating safeguards where individual accounts are not technically feasible. Closure requires verified account configurations, shared-account disposition, access approvals, MFA enforcement, and attributable privileged activity records. No remediation has been approved, performed, or validated.
A-004 | R-004 | Develop and obtain approval for an enterprise cybersecurity risk management policy and centralized risk register. Define standardized risk identification and scoring criteria, assigned risk owners, treatment and acceptance approval authorities, periodic review requirements, escalation thresholds, and leadership reporting procedures. Identify and document the initial risk population, train responsible personnel, and establish recurring governance reviews. Validate implementation and operation before recommending remediation closure. | IT Security Manager - Proposed | Pending approval | Proposed |  |  |  | Pending validation |  | Requires leadership sponsorship, confirmation of existing risk management practices, agreement on risk ownership and acceptance authority, coordination with relevant business units and third-party stakeholders, approval of assessment criteria, and allocation of resources for implementation and ongoing reviews. Closure should be supported by an approved policy, operational risk register, documented ownership and treatment decisions, evidence of training or communication, and records demonstrating completed risk reviews and appropriate escalation. All activities remain proposed, no approval, implementation, or closure validation has occurred.
Formulas:
Days overdue = IF([Action ID]="","",IF(ISNUMBER([Target date]),IF([Workflow status]="Completed",0,MAX(0,TODAY()-[Target date])),""))
REMEDIATION TRACKER
CYBERSECURITY
GRC PORTFOLIO
01 Dashboard
02 Risk register
03 Controls
04 Evidence
05 Remediation
06 Scoring
07 Guide

## Scoring Methodology
GRC PROJECT 01 / TRAINING WORKSPACE / FOUR SIMULATED RISKS / EVIDENCE AND APPROVAL PENDING
Proposed training rubric — requires project approval. Inherent and residual score = likelihood × impact. No residual score is estimated.
Level | Likelihood (proposed) | Impact (proposed) | Interpretation
1 | Rare | Minimal | Limited disruption
2 | Unlikely | Minor | Manageable local disruption
3 | Possible | Moderate | Meaningful service or business disruption
4 | Likely | Major | Material operational or information harm
5 | Almost certain | Severe | Extensive or sustained business harm
Band | Minimum score | Maximum score
Moderate | 6 | 11
High | 12 | 19
Critical | 20 | 25
Low | 1 | 5
Scoring bands: Low starts at 1. Edit the Moderate, High and Critical minimums in F16:F18; maximums calculate from the next band. Minimums must be increasing whole numbers between 2 and 25. All four assessments are simulated and pending validation.
Design effectiveness: the policy and configuration could meet the objective if followed. Operating effectiveness: dated evidence shows the control actually worked over an agreed period. Configuration alone does not establish consistent operation.
Validation requires a confirmed scope, traceable evidence, documented testing and reviewer approval. A validated status is a user-entered conclusion and must be supported. Proposed owners, treatments and target dates require approval. Risk acceptance requires an authorized decision.
SCORING METHODOLOGY
CYBERSECURITY
GRC PORTFOLIO
01 Dashboard
02 Risk register
03 Controls
04 Evidence
05 Remediation
06 Scoring
07 Guide

## Instructions
GRC PROJECT 01 / TRAINING WORKSPACE / FOUR SIMULATED RISKS / EVIDENCE AND APPROVAL PENDING
01 Start with scope
Confirm the applications, accounts, repositories and governance processes covered by each of the four risks. Record confirmed facts and their sources separately from assumptions in Risk Register. The initial source is the user-provided fictional scenario.
02 Edit the assessment
Edit input columns and retain formulas. Likelihood and impact accept whole numbers 1–5; supply both values. Blank residual inputs remain unassessed. Edit Moderate, High and Critical minimum thresholds on Scoring Methodology. Band maximums calculate automatically; invalid threshold order is flagged.
03 Gather and assess evidence
E-001–E-004 are planned requests, not collected evidence. Enter dates, custodian, secure location and reviewer only when known. Use C-001–C-004 to document design and operating tests separately. Validate conclusions only after evidence and review support them.
04 Agree the response
Confirm proposed owners and treatment decisions. Obtain approval before scheduling or implementation. Record completion only after work occurs. Closure requires a valid completion date and one primary evidence ID for the same risk. That evidence record must be reviewed and validated, with a received date, location and reviewer. Its location may reference a package of supporting files. Days overdue stays blank without a target date.
05 Explore the dashboard
Use the left sidebar on every page. The current section is highlighted in cyan; Dashboard returns to the overview. Four dedicated columns keep navigation clear of the data. Bottom worksheet tabs remain hidden. Mint dropdowns filter risk views. Native charts include hidden source data and update when inputs change.
06 Add records and keep formulas
100 prepared rows are available on each tracker (rows 7–106). Fill an existing blank row and retain formula columns. Risk IDs must be unique; use stable IDs to link the trackers. Beyond row 106, extend tables, formulas, validation and dashboard ranges together.
07 Input and formula cues
Pale blue fields are editable; gray fields calculate. Risk assessment notes in X7:X10 combine a calculated score summary with the scenario explanation. Edit their wording in the formula bar and preserve the score references. Fixed-choice fields have dropdowns. Ratings use green for Low, yellow for Moderate, red for High and dark red for Critical. Pasted values can bypass validation.
08 Substantive inputs still needed
Actual affected scope; supporting evidence and assessment period; assessor and reviewer; approved owner and treatment; approved action and target date; tested residual likelihood and impact. Leave these blank or explicitly pending until supplied.
INSTRUCTIONS
CYBERSECURITY
GRC PORTFOLIO
01 Dashboard
02 Risk register
03 Controls
04 Evidence
05 Remediation
06 Scoring
07 Guide